## Taskforce toolkit
Stakeholder engagement plan template
Plan your stakeholder engagement by using the template in this spreadsheet. You should maintain your Stakeholder Engagement Plan as a living document that is iterated as your engagement progresses. An example has been completed below but you should use and adapt the template to your Taskforce's needs.
Get started
Stakeholder engagement plan example
Stakeholder | Purpose of engagement | Influence/impact |  | Strategy to engage | Key concerns | Timing/frequency
Jane Smith and John Citizen / PM&C | Jane and John are in the BAU team to which the taskforce will handover the policy work for implementation. Engage to get their early buy-in to the work for the taskforce and share reasons for decision-making. | High influence/ high impact |  | Initial discussion on Taskforce scope; provide regular updates on findings; seek input into draft deliverables. | Concerned about resourcing impost to implement taskforce recommendations. Assumption: that Jane and John's area is the most suitable one to implement recommendations. | Initial meeting scheduled for 13 January 2021. Regular meetings every second Tuesday or email update where meeting is not possible. Final evaluation and handover to take place one week before closure of Taskforce.

## Stakeholder Engagement Plan
Stakeholder engagement plan
Stakeholder | Purpose of engagement | Influence/impact | Strategy to engage | Key concerns | Timing/frequency
Name of stakeholder/ organisation | Why/on which issues are you consulting the stakeholder? | How high/low is the stakeholder's influence and impact on the taskforce's work and objectives? | How will the taskforce engage the stakeholder and what does the taskforce expect from the stakeholder? | What are the stakeholder's key concerns? Are you making any assumptions that need to be checked? | When/how often will the stakeholder be engaged?